## Asset Register
Emerald Financial Solutions Ltd
Cybersecurity Risk Assessment - Asset Register
Prepared By: Thenuki Munasinghe
Date: July 2026
A | B | C | D | E | F | G | H | I | J | K | L | M | N |  | O | P
[15 empty] | Risk If | Notes
Asset ID | Asset | Asset | Owner | Department | Location | Quantity | Value | Criticality | Confidentiality | Integrity | Availability | Replacement | Current |  | Compromised
|  | Category | [9 empty] | Cost | Security | Controls
HW-001 | Employee | Hardware | IT Manager | All Department | Staff Areas | 45 | Medium | High | High | High | High | 1300€ | - |  | - | -
Laptop
HW-002 | Desktop PCs | Hardware | IT Manager | Finance/IT | Finance/IT | 5 | Medium | High | High | High | Medium | 1000€ | - |  | - | -
Office
HW-003 | File Server | Hardware | IT Manager | IT | Server Room | 1 | High | Critical | Critical | Critical | Critical | 8000€ | - |  | - | -
HW-004 | NAS Backup | Hardware | IT Manager | IT | Server Room | 1 | High | Critical | High | High | High | 3000€ | Restrict |  | Backup | Disaster Recovery
[13 empty] | access |  | Failure
NET-001 | Firewall | Network | IT Manager | IT | Server Room | 1 | High | Critical | High | High | High | 2500€ | Firewall Rules |  | Network | Perimeter Security
Compromised
NET-002 | Business Router | Network | IT Manager | IT | Server Room | 2 | High | High | Medium | High | High | 1000€ | Secure Configuration |  | Internet | Connects to ISP
Disruption
NET-003 | Managed Network | Network | IT Manager | IT | Server Room | 2 | High | High | Medium | High | High | 1200€ | Restrict |  | Internal | Office network connectivity
| Switches | [11 empty] | access |  | Disruption
NET-004 | Wi-Fi AP | Network | IT Manager | IT | Office | 3 | Medium | High | High | High | High | 300€ | Secure WiFi |  | Unauthorized | Office Wireless
[15 empty] | Remote | Networks
Access
CLD-001 | Microsoft 365 | Cloud Service | IT Manager | All Department | Cloud | 45 | Critical | Critical | High | High | High | 5000€ | Company Accounts |  | Data breach | Email & Collaboration
password protection
NET-005 | Company VPN | Network Service | IT Manager | All Department | Cloud | 1 | High | Critical | High | High | High | 2000€ | VPN authentication |  | Unauthorized Access | Supports Hybrid Working
DAT-001 | Customer Financial | Information | Compliance Manager | Finance | File Server | 2500 Records | Critical | Critical | Hgih | High | High | 50000€ | Restricted Access |  | Data breach | Most valuable
| Information | [13 empty] | Fraud | Asset of Company
DAT-002 | Employee HR | Information | HR Manager | HR | HR Office | 45 Records | High | High | High | High | Medium | 10000€ | HR Access Control |  | Privacy Breach | Confidentiality Information
Records
INF-001 | Company Website | Infrastructure | IT Manager | IT | Internet | 1 | Medium | High | Medium | High | High | 3000€ | HTTPS & Firewall |  | Website Outage | Public Facing Business Service
Protection

## Asset Summary
Metric | Result
Total Assets | 13
Hardware Assets | 4
Network Assets | 5
Cloud Services | 1
Information Assets | 2
Infrastructure Assets | 1
Critical Assets | 6
Assets By Category

## Threat Model
Threat-ID | Threat | Description | Likelihood | Impact | Affected Assets | Current Controls | Recommended Controls
THR-001 | Phishing Attack | An employee receives a fraudulent | High | High | HW-001, CLD-001, DAT-005 | Company email accounts, endpoint protection | Implement MFA, phishing awareness training
|  | email designed to trick them into clicking |  |  |  |  | and enhanced email filtering.
THR-002 | Ransomware | Malware encrypts company files | Medium | Critical | HW-001, HW-003, HW-004, DAT-001, DAT-002 | Endpoint protection, firewall and NAS backups. | Implement tested offline backups,
|  | and prevents employees from accessing |  |  |  |  | stronger endpoint protection,
|  | protected information |  |  |  |  | incident response procedures.
THR-003 | Weak Passwords | Employees use weak, reused or | High | High | CLD-001, NET-005, HW-001 | Company accounts and password policies | Introduce stronger password requirements, MFA
easily guessed passwords
THR-004 | Business Email Compromise | An attacker gains access to an employee's email | Medium | Critical | CLD-001, DAT-005 | Microsoft 365 accounts and password protection | MFA, email monitoring, payment verification procedures
account and uses it to impersonate the employee
THR-005 | Malware Infection | Malicious software is installed on an employee device | Medium | High | HW-001, HW-002, DAT-001 | Endpoint protection and firewall. | Improve endpoint detection, application controls and employee security awareness.
through a malicious attachment, website or downloaded file.
THR-006 | Laptop Theft | A company laptop is stolen from the office | Medium | High | HW-001, DAT-001 | Access controls, VPN and endpoint protection. | Device encryption, remote wipe capability, laptop security locks
THR-007 | Unauthorised Network Access | An attacker gains unauthorised access to the internal | Medium | Critical | NET-001, NET-002, NET-003, HW-001, HW-003 | Firewall, managed switches and restricted server room. | Network segmentation, stronger access controls, network monitoring and
|  | network and attempts to compromise company systems. |  |  |  |  | regular vulnerability assessments.
THR-008 | Unauthorised Physical Access | An unauthorised person enters staff or restricted | Medium | High | HW-001, HW-003, NET-001, DAT-001 | Staff access cards, reception sign-in, CCTV and restricted server room | Mandatory visitor escorting, quarterly access-card
|  | areas and gains access to equipment or confidential information. |  |  |  |  | reviews and additional server-room CCTV.
THR-009 | VPN Account Compromise | An attacker obtains an employee's VPN credentials | Medium | High | NET-005, HW-003, DAT-001 | Company VPN and user authentication. | MFA, VPN monitoring and conditional access controls.
and uses them to access the company resources
THR-010 | Insider Threat | An employee intentionally or accidentally accesses | Low | Critical | DAT-001, DAT-002, DAT-003, CLD-001 | Access controls and departmental permissions. | Least-privilege access, access reviews, employee monitoring and security awareness training.
modifies or discloses confidential company information.

## Risk Matrix
Thret ID | Threat | Likelihood | Impact | Risk Score | Risk Level
THR-001 | Phishing Attack | 5 | 5 | 25 | Critical
THR-002 | Ransomware | 3 | 5 | 15 | High
Critical
THR-003 | Weak Passwords | 5 | 4 | 20
THR-004 | Business Email Compromise | 3 | 5 | 15 | High
THR-005 | Malware Infection | 3 | 4 | 12 | High
THR-006 | Laptop Theft | 3 | 4 | 12 | High
THR-007 | Unauthorised Network Access | 3 | 5 | 15 | High
THR-008 | Unauthorised Physical Access | 3 | 4 | 12 | High
THR-009 | VPN Account Compromise | 3 | 4 | 12 | High
THR-010 | Insider Threat | 2 | 5 | 10 | Medium

## Gap Analysis
ID | Security Area | Current State | Desired State | Gap | Priority | Recommended Action | Owner | Timeline
GAP-001 | Multi-Factor Authentication | MFA is not currently implemented | MFA enabled for all users | Accounts rely mainly on passwords | Critical | Implement MFA for Microsoft 365 and VPN | IT Manager | Month 2
GAP-002 | Password Security | Basic password protection | Strong password policy and secure authentication | Password security could be improved | High | Introduce strong password requirements and password manager guidance | IT Manager / HR | Month 1
GAP-003 | Security Awareness | No formal recurring security awareness programme | Annual and periodic security awareness training | Employees may be vulnerable to phishing and social engineering | High | Introduce cybersecurity awareness training | HR Manager / IT Manager | Month 3
GAP-004 | Phishing Protection | Basic email security | Advanced email filtering and phishing protection | Increased risk of malicious emails reaching employees | High | Improve Microsoft 365 email security controls | IT Manager | Month 2
GAP-005 | Endpoint Protection | Endpoint protection is implemented | Centrally managed endpoint detection and response | Limited advanced monitoring | High | Implement improved endpoint detection and response | IT Manager | Month 3
GAP-006 | Backup Testing | Backups are performed but regular recovery testing is not confirmed | Backups regularly tested and verified | Recovery reliability is uncertain | Critical | Perform scheduled backup restoration tests | IT Manager | Month 5
GAP-007 | Offline Backups | NAS and backup drives are available | Protected offline/isolated backups maintained | Backups may be exposed to ransomware | Critical | Introduce offline or immutable backup copies | IT Manager | Month 5
GAP-008 | Network Segmentation | Internal network is broadly connected | Network separated into appropriate security zones | Attackers could move between systems more easily | High | Implement network segmentation/VLANs | IT Manager | Month 4
GAP-009 | Access Reviews | Access is managed but regular reviews are not confirmed | Quarterly access reviews performed | Unnecessary access may remain active | High | Conduct quarterly user and access reviews | IT Manager / HR | Month 2
GAP-010 | Visitor Management | Visitors sign in but are not always escorted | Visitors escorted in restricted areas | Visitors could access restricted areas | High | Introduce mandatory visitor escorting | Facilities Manager | Month 1
GAP-011 | Server Room Monitoring | No dedicated CCTV in server room | Server room monitored by CCTV | Physical security monitoring gap | High | Install server-room CCTV | Facilities Manager | Month 4
GAP-012 | Clean Desk | No formal clean desk policy | Formal clean desk policy implemented | Confidential documents may be exposed | Medium | Introduce and enforce clean desk policy | HR Manager | Month 3
GAP-013 | Laptop Security | Laptop locks are not currently used | Laptops physically secured where appropriate | Increased physical theft risk | Medium | Provide laptop security locks | IT Manager | Month 3
GAP-014 | Incident Response | Incident response procedures require formalisation | Documented and tested incident response plan | Response may be inconsistent during an incident | Critical | Develop and test incident response plan | IT Manager / Project Manager | Month 1
GAP-015 | Vulnerability Management | Regular vulnerability assessments are not confirmed | Regular vulnerability scanning and remediation | Vulnerabilities may remain undetected | High | Introduce quarterly vulnerability assessments | IT Manager | Month 4

## Recommendations
ID | Problem | Business Impact | Recommendation | Estimated Cost | Priority | Timeline | Owner | Related Risk
REC-001 | MFA is not implemented for all users | Compromised passwords could allow unauthorised access to company systems and data | Implement MFA for Microsoft 365, VPN and other supported services | 3000 | Critical | Month 2 | IT Manager | Phishing / VPN Account Compromise
REC-002 | Password security requires improvement | Weak or reused passwords increase the risk of account compromise | Implement a strong password policy and approved password management solution | 1500 | High | Month 1 | IT Manager / HR | Weak Passwords
REC-003 | Security awareness training is not formalised | Employees may fall victim to phishing and social engineering | Introduce annual security awareness training and simulated phishing exercises | 2000 | High | Month 3 | HR Manager / IT Manager | Phishing
REC-004 | Email security controls require improvement | Malicious emails could lead to credential theft or malware infection | Strengthen Microsoft 365 email filtering and anti-phishing controls | 3000 | High | Month 2 | IT Manager | Phishing / Business Email Compromise
REC-005 | Advanced endpoint monitoring is limited | Malware may remain undetected and spread across devices | Implement centrally managed endpoint detection and response | 6000 | High | Month 3 | IT Manager | Malware Infection / Ransomware
REC-006 | Backup recovery testing is not confirmed | Failed backups could prevent recovery after ransomware or system failure | Perform scheduled backup restoration tests | 1000 | Critical | Month 5 | IT Manager | Backup Failure / Ransomware
REC-007 | Backup protection against ransomware requires improvement | Attackers could compromise accessible backups | Introduce offline or immutable backup copies | 4000 | Critical | Month 5 | IT Manager | Ransomware / Backup Failure
REC-008 | Internal network segmentation requires improvement | Attackers could move between systems after gaining access | Implement VLANs and appropriate network segmentation | 5000 | High | Month 4 | IT Manager | Unauthorised Network Access
REC-009 | Physical visitor controls are inconsistent | Visitors could gain access to restricted areas or sensitive information | Introduce mandatory visitor escorting | 500 | High | Month 1 | Facilities Manager | Unauthorised Physical Access
REC-010 | Server room has no dedicated CCTV | Physical attacks or unauthorised access may not be detected | Install CCTV covering the server room entrance/area | 1500 | High | Month 4 | Facilities Manager | Unauthorised Physical Access
REC-011 | No formal clean desk policy | Confidential documents could be viewed or removed by unauthorised individuals | Introduce and enforce a clean desk policy | 500 | Medium | Month 3 | HR Manager | Data Breach
REC-012 | Incident response procedures require formal testing | The company may respond slowly or inconsistently during a major incident | Conduct an incident response exercise and update the response plan | 1500 | Critical | Month 1 | Project Manager / IT Manager | Ransomware / Data Breach
|  |  | TOTAL | 29500

## Implementation Roadmap
Task ID | Implementation Activity | Related Recommendation | Owner | Priority | Start | End | Cost | Status | Activity | K | L | M | N | O | P
IMP-001 | Approve and implement Password Policy | REC-002 | IT Manager / HR | High | Month 1 | Month 1 | 1500 | Planned |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
IMP-002 | Formalise Incident Response Plan | REC-012 | Project Manager / IT Manager | Critical | Month 1 | Month 1 | 1500 | Planned | Password Policy
IMP-003 | Introduce mandatory visitor escorting | REC-009 | Facilities Manager | High | Month 1 | Month 1 | 500 | Planned | Incident Response Plan
IMP-004 | Implement MFA | REC-001 | IT Manager | Critical | Month 2 | Month 2 | 3000 | Planned | Visitor Escorting
IMP-005 | Improve email security controls | REC-004 | IT Manager | High | Month 2 | Month 2 | 3000 | Planned | MFA
IMP-006 | Deliver security awareness training | REC-003 | HR Manager / IT Manager | High | Month 3 | Month 3 | 2000 | Planned | Email Security
IMP-007 | Implement endpoint detection and response | REC-005 | IT Manager | High | Month 3 | Month 4 | 6000 | Planned | Security Awareness Training
IMP-008 | Introduce clean desk policy | REC-011 | HR Manager | Medium | Month 3 | Month 3 | 500 | Planned | Endpoint Protection
IMP-009 | Implement network segmentation | REC-008 | IT Manager | High | Month 4 | Month 4 | 5000 | Planned | Clean Desk Policy
IMP-010 | Install server-room CCTV | REC-010 | Facilities Manager | High | Month 4 | Month 4 | 1500 | Planned | Network Segmentation
IMP-011 | Improve and test backup systems | REC-006 / REC-007 | IT Manager | Critical | Month 5 | Month 5 | 5000 | Planned | Server CCTV
IMP-012 | Conduct cybersecurity audit and review | REC-012 | Project Manager / Compliance | Critical | Month 6 | Month 6 | 0 | Planned | Backup Improvements
Cybersecurity Audit
Implementation Budget
A | B
Estimated Implementation Cost | 30000
Contingency (10%) | 3000
Total Project Budget | 33000
Note: All costs are indicative estimates prepared for portfolio planning purposes.
Actual costs would require supplier quotations before implementation.

## Dashboard
EMERALD FINANCIAL SOLUTIONS LTD
Cybersecurity Risk Assessment Dashboard
2026-07-01
TOTAL ASSETS |  | TOTAL RISKS |  | CRITICAL RISKS | PROJECT BOX | PROGRESS
13 |  | 10 |  | 6 | 33000 | 0%
Key assets assessed |  | Threats assessed |  | Requires immediate action | 6-month implementation plan | Project Not Started
|  |  | Recommendation | Cost
Risk Level | Number |  | Password Policy | 1500
Critical | 2 |  | Incident Response | 1500
High | 7 |  | Visitor Escorting | 1000
Medium | 1 |  | MFA | 3000
Low | 0 |  | Email Security | 3000
Total | 10 |  | Security Training | 2000
|  |  | Endpoint Protection | 6000
KPI | Value |  | Clean Desk Policy | 500
Total Assets | 13 |  | Network Segmentation | 5000
Total Risks | 10 |  | Server CCTV | 1500
Critical Risks | 2 |  | Backup Improvements | 5000
Project Budget | 33000 |  | Cybersecurity Audit | 0
Implementation Progress | 0% |  |  | 30000

## Budget
Cybersecurity Security Improvement Budget
Organisation: Emerald Financial Solutions Ltd
Project: Cybersecurity Risk Assessment & Security Improvement Project
Budget Type: Estimated Implementation Budget
Currency: EUR (€)
Planning Period: Year 1
1. Budget Summary
Budget ID | Security Area | Estimated Cost (€) | Priority | Risk Addressed
BUD-001 | Identity & Access Management | 1500 | Critical | Phishing, VPN Account Compromise | s
BUD-002 | Security Awareness & Phishing Training | 1200 | Critical | Phishing
BUD-003 | Endpoint Security | 3000 | High | Malware, Ransomware
BUD-004 | Email Security | 2000 | High | Phishing, Business Email Compromise
BUD-005 | Backup & Disaster Recovery | 2500 | Critical | Ransomware, Data Loss
BUD-006 | Network Security | 2000 | High | Unauthorised Network Access
BUD-007 | VPN & Remote Access Security | 1000 | High | VPN Account Compromise
BUD-008 | Physical Security | 1500 | High | Unauthorised Physical Access
BUD-009 | Security Policies & Staff Training | 800 | Medium | Insider Threat, Human Error
BUD-010 | Security Monitoring & Testing | 1500 | Medium | Ongoing Security Risks
| TOTAL ESTIMATED BUDGET | 17000